## Sheet1
Week (2012) | Task
3 | Create thesis report
Read Viet Thuy Vu's dissertation
Read Merill Skolnik's radar handbook
Read Thomas Sjögren's licenciate
Start writing thesis background chapter and add background to thesis proposal
4 | Read selection of recent SAR papers
Finish thesis proposal
More writing on thesis background chapter
5 | Learn how to use Scilab
Model building
"Finish" background chapter in thesis report
6 | Model building
7 | Model building
Update thesis report with text about SAR code (part of methodology chapter)
8 | Validate and evaluate Scilab model
9 | Validate and evaluate Scilab model
10 | Specify parameter requirements
Include results in report
11 | Make an effort to improve SAR algorithms
Create chapter in thesis report on improvement to SAR algorithms
12 | Apply real radar data in simulation model
Evaluate results
Add real data results to report
13 | Continue real data evaluation
14 | Do we have acceptable system performance?
15 | Finish simulation model and results in report
16 | Start real time implementation of SAR algorithms
17 | More real time implementation work
18 | More real time implementation work
19 | Reflect on whether we really have acceptable system performance
20 | Finish thesis report
21 | Finish thesis report
21 | Create thesis presentation
22 | Thesis presentation
-s'-s
aoeaoeaeoaeoaeoaeoaoaaaoeueuuuuuuuuuuuuuu¨,
ssssoooooooooooeeeeeeeeeooooooooooo--------------------
-'''''eeeeeeeeeneneoaeaoeaoe